## 4 March 19
Participants | Bruno Minjauw, gFSC ; Cyril Lekief, ACF; Angela Hinrichs, FAO; Carine Malardeau, IFRC; Elisa Persico, WFP; Emilie Poisson, Impact; Philippa Young, OXFAM
Agenda points | Action points | Follow up
Next gFSC Partner’s meeting | 1) possibility of having Paris as venue for the next Partners’ meeting (21-23 May 2019) (tbc) 2) Welthungerhilfe also volunteered to host it: Bruno will contact Barbel Mosembach to further inquire.
Questionnaire for the Cluster Coordinators | 1. Comments from SAG members were received, and approved. 2. Share the amended version for final approval by the SAG 3. The results of the survey will be used: as point of discussion during the next Partners’ Meeting, as key element for the strategic plan and to develop the working groups | 1) 2) 3)
Mid-term review | 1) Approved by all SAG members 2) It will be uploaded on the gFSC website and shared using the infocluster email address. | 1) 2)
4. Email address SAG | 1) A dedicated email address has been created for the SAG: sag@fscluster.org 2) all emails received will be shared will all SAG Members either forwarding it or discussing about it during the next SAG conference call 3) This email address is for increased communications amongst global members. No invitations regarding the Cluster’s activities will be sent from the SAG email address. The Minutes of the SAG’s meetings/conference calls will be shared with Partners’ using the SAG email address.
AOB | 1) Annual Report

## 22 May 19
Participants | Bruno Minjauw, gFSC ; Cyril Lekief, ACF; Angela Hinrichs, FAO; Carine Malardeau, IFRC; Elisa Persico, WFP; Philippa Young, Oxfam; Katie Rickard, REACH; Riccardo Suppo, GFSC
Agenda points | Action points | Follow up
1. General SAG and global team updates | 1) list partners on website and their specific status (Full member, Associate or Observer) 2) Letter will be sent by gFSC Cluster Coordinator to partners which applications have not been successful or if the status chosen was inadequate. 3) The SAG will review and validate new applications When new strategy is inaugurated, partners will need to review membership (partners need to reapply every 3 years). 4) Cyril to share dual management in ACF structure with Bruno to help with global/country level mgmt. of coordinators. Carine to cross-check with Shelter cluster. 5) a project could be written for the GFSC similar to the WASH example 6) Cyril attended the meeting on 4/5/6 June at ACF to see how WASH does it with field support team. 7) Bruno to ensure that Coordinator elect their representatives ASAP as the work on the Strategic Plan is starting.
2. SAG achievements and presentation for gFSC Partner meeting | 1. need to develop SAG recommendations on this by the end of June and send back to coordinators. 2. Global support unit can work on a first draft to submit to SAG. First draft outline by end of June. 3. The results of the survey will be used: as point of discussion during the next Partners’ Meeting, as key element for the strategic plan and to develop the working groups. 4. Webinar to comment in early July and with partners. 5.First draft will be completed by end of September with one month for partners to comment. 6. Next face to face SAG in Geneva 29/30th August. 7. Next partners meeting is 26/27/28th November at WFP 8. Partner meeting: 3 groups: - Global Network Against Food Crises: SAG needs to engage with FAO and WFP on how NGOs can engage. Some partners have written to FAO to ask about engagement but have not received a reply. - FAM: need to work out ways to engage with this. The cluster should have more direct representation with the FAM. Agencies are finding it an opaque process. Action point: let’s improve communication on this. - CCPM: cannot move forward on this as the report has not been received (quota of 50% not met). - Private sector engagement: Bruno participated in a conference about this and can share his back to office report on this. In Ukraine big PS cement company is sitting in HCT. They created a foundation and come to FSC meetings. Various conversations around engagement with Silicon Valley and food companies though no progress on this subject due to legal issues and branding etc.

## 3 June 19
Participants | Bruno Minjauw, gFSC ; Cyril Lekief, ACF; Angela Hinrichs, FAO; Carine Malardeau, IFRC; Elisa Persico, WFP; Emilie Poisson, Impact; Philippa Young, OXFAM; Katie Rickard, REACH; Damien Joud, gFSC
Agenda points | Action points | Follow up
Update about the governance of the gFSC | 1) gFSC Staff will be seconded to WFP 2) Special account to run the gFSC. Additionally, a budget will be designed for the 15 countries for the support team and surge team. This budget will be like a revolving funds where the gFSC budget will advance the funds to COs who will refund the cost of the FSC team 3) For these 15 countries, the functional supervision will be under the CLAs while the hierarchical supervision will be under the gFSC (TBC). 4) Carine to crosscheck with Shelter cluster regarding the dual management.
Cluster Coordinator in SAG | 1. gFSC (Eleonora) to send the link to the Cluster coordinator and Cluster co-coordinator for the SAG election. | 1) 2) 3)
CCPM report | 1) gFSC (Eleonora) to conduct the CCPM analysis by Friday 7th June; 2) gFSC to send it to SAG members for their review/approval; 3) use findings for the strategy | 1) 2)
Cluster coordinator’s survey and development of recommendations | 1) The gFSC support team to write the report and then send it to the SAG by 14 June 2) The document will be available on the FSC website. The link will be shared 3) Addition/changes to be made in track mode by SAG members meetings/conference calls will be shared with Partners’ using the SAG email address.
5. Review of 18 applications | The gFSC (Walter) will prepare a table for the new applications. The SAG members will review and validate. Deadline is 1st July 2019 (next SAG meeting)
Global Report on Food Crises Responses and Prevention | Bruno to write to Dominique for Katie and Philippa’s participation
Cash coordination in Zimbabwe | 1) gFSC to check with the CC what the blockages are; who is the lead agency of the CWG in order to push and when it is expected to get the MPCG guideline finalised 2) Cyril to share the email and file it in a shared folder

## 1 July 19
Participants | Bruno Minjauw, gFSC ; Carine Malardeau, IFRC ; Philippa Young, Oxfam; Katie Rickard, REACH ; Damien Joud, gFSC
Agenda points | Action points | Follow up | Priority
CCPM | 1) the gFSC will check about the countries where the number of participants are over 100% 2) the gFSC will share the questionnaire to the SAG member. 3) An example of the results will be shared | 1) done - (issue is due to miscaculation at CO level) 2) done 3) done (Haiti)
Cluster Coordinator in SAG | 1. Select the first sixth candidates (the ones who get the highest number of votes) 2. Ask them if they want to be in the SAG 3. Check if the CLAs are in agreement 4. Organise the vote with one vote per country | 1. done 2. done 3. done partially - waiting for Haiti-CLAs response 4. pending
gFSC membership | 1) Damien to share the results (due diligence and activeness) 2) gFSC to send the list of members to the SAG for their vote (online | 1. done 2. done - nobody voted yet
Cluster coordinator survey | 1) The gFSC support team to share the report 2) The document will be available on the FSC website. The link will be shared Addition/changes to be made in track mode by SAG members | 1. still pending 2. not done
Update about the governance of the gFSC | no action points
Review of the gFSC strategy | 1. Based on their comments, the gFSC support team will review the document before sharing it with the SAG before 07th July 2. SAG members to provide their comments by 12th July 3. A webinar with gFSC members to be organised by end July/early August 4. Workshop scheduled end of August (invitation sent by Carine) | 1. done (at at later date) 2. pending 3. pending 4. invitation sent by Carine - done
AOB - Update from the gFSC support team | Organised monthly call planning for the 15 highest priorities countries Monthly call tracking sheet with key actions Tracking mission and deployment

## 5 Aug19
Participants | Philippa Young, Oxfam; Damien Joud, gFSC Angela Hinrichs, FAO; Elisa Persico, WFP
Agenda points | Action points | Follow up | Priority
Review of the gFSC strategy | 1. comment still pending from SAG members 2. one main comment: vision should be agreed by everybody before the strategy 3. WFP: vision needs to highlight the work of the FSC in humanitarian setting
gFSC membership | 1) remove members who are currently members (gFSC secretariat) 2) circulate again the link for the vote (gFSC secretariat) | 1) done 2) link circulated again on 20/08 to SAG
gFSC partners' meeting report | 1) no action point 2) positive comment regarding the interactive format

## 2 Sept 19
no SAG meeting as there was a SAG workshop on the strategy on 28 and 29 August

## 7 Oct 19
Participants | Bruno Minjauw, gFSC ; Carine Malardeau, IFRC ; Philippa Young, Oxfam; Angela Hinrich, FAO; Damien Joud, gFSC; Elisa Persico, WFP
Agenda points | Action points | Follow up | Priority
gFSC partners' meeting - agenda | 1)there were some comments from SAG members regarding the agenda (outline objectives, PSEA session, etc) | the agenda was revised and shared to the gFSC partners.
FSC Strategy | 1) there were some additional comments and discussions on the strategy 2) next steps for the strategy: 2.1. English edit 2.2. share it with the FSC and partners 2.3. organise a webinar 2.4. launch the strategy during the gFSC partners' meeting + organise a discussion | 2.1. done but need a more thorough one 2.2. done - strategy shared 2.3. webinar: save the date email sent for the webinar which will be organised on 30 October 2.4. pending
SAG election | 2 slots for the SAG available and election to be organised during the next gFSC partners' meeting 1) email for seeking interest 2) election to be organised (paper or electronic) | 1) email sent 2) pending
gFSC membership | 1) all SAG members to vote 2) Damien to send to the SAG members the final vote 3) Conference call with SAG members to finalise decisions for gFSC membership | 1. done - vote completed 2. done - final result sent to SAG members 3. pending - invitation by email sent by Damien on 22/10/2019
AOB - Update from the gFSC support team | no AOB
Pending item
Cluster coordinator survey | 1) The gFSC support team to share the report 2) The document will be available on the FSC website. The link will be shared Addition/changes to be made in track mode by SAG members | 1. still pending 2. not done

## 11 Nov 19
Participants | Bruno Minjauw, gFSC ; Carine Malardeau, IFRC ; Philippa Young, Oxfam; Angela Hinrich, FAO; Damien Joud, gFSC; Elisa Persico, WFP
Absent | Cyril Lekiefs, ACF
Agenda points | Action points | Follow up | Priority
gFSC partners' meeting - agenda | 1. the agenda of the meeting was revised and shared. 2. all key note and other speakers are confirmed 3. WG agenda and timing to be finalised | WG agenda and timing to be finalised
FSC Strategy | 1) the webinar was organised on 5 November on with about 18 participants 2) the strategy will be revised based on comments received during the webinar and those received online | 1. share the revised strategy online asap 2. deadline to receive comment on 18 November and finalise final draft before the partners' meeting
SAG election | 1. the message was not very clear and issues with the info@fscluster.org email address as it often goes to the junk box 2. application open until 27 Nov, 12pm 3. candidates to be approached bilaterally | ToR to reviewed after election during the SAG meeting
gFSC membership | 2 approaches: 1) applicants fulfill the criteria or not, 2) if applicant gets 50% or over, considerd as observer - if below, application not accepted For those with 100% vote, they are full members | The day after, Carine reviewed all the applications, according to the criteria. This approach was approved by all the SAG members. Damien to inform applicants based on the decision
SAG meeting (25 November) | proposed agenda for the 25 November: membership gFSC; ToR SAG SAG meeting: lunch at 12.30pm, we will all meet at 12.30pm in FAO main hall
AOB | no AOB
Pending item
Cluster coordinator survey | 1) The gFSC support team to share the report 2) The document will be available on the FSC website. The link will be shared Addition/changes to be made in track mode by SAG members | 1. still pending 2. not done

## 25 Nov 19
Participants | Bruno Minjauw, gFSC ; Carine Malardeau, IFRC ; Philippa Young, Oxfam; Angela Hinrich, FAO; Damien Joud, gFSC; Elisa Persico, WFP
Absent | Cyril Lekiefs, ACF
Agenda points | Action points | Follow up | Priority
gFSC partners' meeting - update | 1. talking points for the opening by the 2 CLAs Directors of Emergencies 2. review the agenda and discuss about the changes (presentation of the Global Network by WFP, DEVCO, FAO and gFSC) 3. SAG presentation: Carine to prepare it.
Workplan SAG | A workplan against the strategic results will be prepared with the new elected members. A Face to Face meeting will take place in January - February
Review SAG ToR | In the last SAG meeting, it was proposed to review the ToR: membership and SAG member duration of mandate. It was agreed that the current ToR is fine (no change made in the ToR) | 1. share the revised strategy online asap 2. deadline to receive comment on 18 November and finalise final draft before the partners' meeting
gFSC membership | Damien informed the candidates (observers, associate and full members)
Next gFSC partners' meeting | May (week 11th to 15th May): TBC
AOB | no AOB
Pending item
Cluster coordinator survey | 1) The gFSC support team to share the report 2) The document will be available on the FSC website. The link will be shared Addition/changes to be made in track mode by SAG members | 1. still pending 2. not done