## Slide 1
1. Finalized Inter-cluster Nutrition Training Package
Product
Purpose: To finalize the ICN training package and to make available this training package for any interested countries
Roles and Responsibilities: WVI, ACF, Oxfam, FAO,WFP, UNICEF, GNC, and gFSC
Link to other WGs: NO
Resources: gFSC & GNC secretariat, funding for piloting the training package in 2 countries, commitment from several country clusters to organize, consultant for piloting and reviewing the package, alongside WG members
Timeline: September 2018

## Slide 2
1. Finalized Inter-cluster Nutrition Training Package
Product
Purpose: To finalize the ICN training package and to make available this training package for any interested countries
Activities undertaken:
Preparation of the draft material (consultant + partners)
Piloting in Ethiopia and Nigeria completed
Workshop to improve the package.
Implementation in South Sudan
Progress:
Finalized
Way forward (May 2019): - Improved version with support of a training specialist – REdR (trainer’s manual and a participants reference book).
- Follow up with the Global Clusters coordinators’ group (Jan)
Timeline: September 2018
Notes: Integrated Inter-cluster Training Package for Nutrition outcomes

## Slide 3
2. Monitoring tool for the training
Product
Purpose: To assess the performance of the implemented trainings at country level (at least 2 countries)
Roles and Responsibilities: WVI, ACF, Oxfam, FAO,WFP, UNICEF, GNC, gFSC
Link to other WGs: NO
Resources: consultant, members, country cluster coordinators
Timeline: Dec. 2018

## Slide 4
2. Monitoring tool for the training
Product
Purpose: To finalize the ICN training package and to make available this training package for any interested countries
Activities undertaken:
- Daily and final evaluations and debriefings sessions at each pilot
Progress:
Finalized
Timeline: September 2018

## Slide 5
3. A concept note about ICN training facilitation
Product
Purpose: To fundraise required resources for implementing the training in additional interested countries
Roles and Responsibilities: WVI, ACF, Oxfam, FAO,WFP, UNICEF, GNC, and gFSC
Link to other WGs: NO
Resources: Time from members
Timeline: Dec. 2018

## Slide 6
3. A concept note about ICN training facilitation
Product
Purpose: To fundraise required resources for implementing the training in additional interested countries
Activities undertaken:
- Draft concept note for fundraising elaborated.
Status:
Ongoing
Way forward (May 2019):
Re-circulate and review the concept note in the ICN group;
Identify technical and financial partners.
Timeline: September 2018 (May 2019)

## Slide 7
4. Consult on 1 case study on nutrition integration
Product
Purpose: To assess the feasibility of producing one case study (suggested WoS)
Roles and Responsibilities: WVI, ACF, Oxfam, FAO,WFP, UNICEF, GNC, gFSC
Link to other WGs: NO
Resources: Time from members and from sectors’ coordinators and members, funds for publication
Timeline: December 2018

## Slide 8
4. Consult on 1 case study on nutrition integration
Product
Purpose: To assess the feasibility of producing one case study (suggested WoS)
Activities undertaken:
Funding challenges
Progress:
To be started
Way forward (May 2019):
Initiate (3 +) country cases (e.g. Nigeria, Yemen, WoS)
Identify technical and financial partners for the country cases;
GNC to discuss with tech RRT;
Include it in the ICN training CN, as needed.
Timeline: December 2018 (Dec 2019)

## Slide 9: Summary
Product 1. Finalized Inter-cluster Nutrition Training Package
May 2019
Purpose: To finalize the ICN training package and to make available this training package for any interested countries
Product 2. Monitoring tool for the training
Completed
Purpose: To assess the performance of the implemented trainings at country level (at least 2 countries)
Product 3. A concept note about ICN training facilitation
May 2019
Purpose: To assess the performance of the implemented trainings at country level (at least 2 countries)
Product 4. Consult on cases study on nutrition integration
December 2019
Purpose: To assess the performance of the implemented trainings at country level (at least 2 countries)
Cash and Nutrition Working Group collaboration will be discussed with wider GNC