## Slide 1: Cash & Markets WG Report to Plenary
Global Partners Meeting
Rome, 23-24 May 2019

## Slide 2
Update of Achievements as of May 2019 |  |  | 
Activity | Achievements in benefit of in-country FSC (what?) | Next steps in benefit of in-country FSC (when? how?) | Leading partners
MPC Guidance Reporting for FSC/FSS | Generic Guidance based on results from FSC Survey drafted Gathering inputs from FSCs – to be incorporated and finalized | FSC MPC Guidance – additional IM component to be added Hold an ad-hoc meeting/webinar to share Include MPC indicators (GB activity) into FSC MPC guidance | FSC MPC Guidance: gFSC; FSC Coordinators and WG members
Cash for Work Guidance | A first draft has been developed by Plan International and FAO and shared with the WG | Guidance to be shared with all FSC/FSS for inputs – make it as practical as possible for CCs | Plan; WVI, FAO; WFP and all WG members
Capacity Building | Webinars for FSC/WG members have been organized throughout - CVA and Protection for FS held in May 2019 (100 attendees!) | Share CVA and Protection resources from the Webinar Organize CVA and Nutrition Webinar | gFSC and all WG members

## Slide 3
Cash & Markets WG Workplan
(As agreed at the May 2019 Partners Meeting)
ACTIVITY Multi-Purpose Cash Guidance on Reporting for Food Security Clusters/Sectors | TIMELINE & PARTNERS June 2019 – gFSC; CCs/IMOs in FSCs at national-level; all WG members
CVA and Risk Webinar – how agencies are conducting risk analysis and informing design and operations | Sept 2019 – CaLP, WFP, WG members
Advocacy at GCCG level for a coherent approach on mainstreaming CVA into HPC review, TORs, MPC Guidance on Reporting – systematic approach for communication to the field | No tight deadline – gFSC, OCHA, all WG members
Localization – sharing and learning from localization experiences from selected countries with focus on CVA and Food Security. | October 2019 – CashCap, gFSC CMWG members