## Slide 1: Programme Quality WG Report to Plenary
Global Partners Meeting
Rome, 23-24 May 2019

## Slide 2
Cash & Markets WG Workplan
(As agreed at the May Partners Meeting)
ACTIVITY Global Food security Indicator Handbook | TIMELINE & PARTNERS December 2019; gFSC, IMPACT, Oxfam, all partners
Methodology repository | Completed. Internal doc available.
Deciding Strategy for 2020 | November 2019.

## Slide 3
Update of Achievements as of May 2019 |  |  | 
Activity | Achievements in benefit of in-country FSC (what?) | Next steps in benefit of in-country FSC (when? how?) | Leading partners
Global Food Security Indicator Handbook | PQWG Updating GFSC Handbook to ensure IPC compatibility and provide clear guidance to improve and streamline M&E reporting. Handbook structure, indicator list and indicator handbook endorsed Indicator first draft of content completed. | First draft of all indicators to be shared with PQWG partners for feedback X2 rounds of feedback Endorsement in November 2019 partner meeting Publication and graphic design late 2019 for publication 2020 | IMPACT, Oxfam
Methodology repository | One stop-shop methodological repository Internal draft available | Finalized. Agreed to keep this as internal document for PQWG and FSC partners | FAO