## Slide 1: Preparedness and Resilience Working Group (PRWG) Report to Plenary
Global Partners Meeting
Rome, 23 - 24 May 2019

## Slide 2
PRWG Workplan
(As agreed at the November Partners Meeting)
Products & Actions:
Glossary on Preparedness and Resilience
Repository for existing e-learning on preparedness & resilience
Business Case on Preparedness
Define the future of the PRWG (e.g. in-country needs and in view of the Early Recovery Cluster transition)
→ Workplan has been adapted taking into account the outcome of the Cluster Annual Needs Assessment Survey

## Slide 3
Update of Achievements as of May 2019 |  |  | 
Activity | Achievements in benefit of in-country FSC (what?) | Next steps in benefit of in-country FSC (when? how?) | Leading partners
Glossary on Preparedness and Resilience | Food Security Terminology Version 2.0 drafted and updated in regard to preparedness and resilience terminologies | Hand document to corporate design experts for layout Food Security Terminology Version 2.0 is uploaded to gFSC webpage and communication to in-country FSC Terminology is maintained as a lively document and if necessary revised once a year Timeline: n.a. | Welthungerhilfe
Repository for existing e-learning on preparedness & resilience | List of 32 resources for e-learning on preparedness & resilience has been compiled | Input from PRWG on further resources will be included Dissemination via gFSC web-page and communication to in-county FSC Timeline: June 2019 | IFRC

## Slide 4
Workplan June - November 2019 |  |  | 
Activity | Achievements in benefit of in-country FSC (what?) | Next steps in benefit of in-country FSC (when? how?) | Leading partners
Share lessons learned on Preparedness, EWEA, Vulnerability Reduction and Resilience | / | Requesting input from all gFSC partners on lessons learned concerning preparedness (particularly EWEA), vulnerability reduction, and resilience Compile final overview and disseminate to in-country FSC Timeline: August 2019 (lessons learned) / November 2019 (final overview and disseminate) Hold webinar on UN Common Guidance on Helping Build Resilient Societies for partners and cluster coordinators Timeline: October 2019 | World Vision & Concern FAO
Re-fresher survey to assess in-country FSC needs | / | To compile single survey with questions from all WGs, to be sent out by PQWG Assess the outcomes and respond to identified needs Timeline: November 2019 | Welthungerhilfe

## Slide 5
Way forward and comments
The PRWG suggests:
To widen the work of the gFSC Preparedness and Resilience Working group to Early Action work, as this is very relevant to the FSC and falls under the topic of preparedness
Future (activities) of PRWG depends on outcome of re-fresher survey