## Slide 1: SAG Update

## Slide 2: SAG achievements (1)
Main activities planned | Progress Update
Hold regular SAG meetings | One day SAG seminar in Early January, Paris (ACF) Monthly SAG calls - 1st Mondays of the months (4) Minutes on the website
Develop agendas of the partners’ meetings | Agenda discussed
Develop an annual SAG work plan | Workplan developed & progress monitored
Review of the 2018 annual report | Review and comments sent to GSU & posted on Website
Review the mid-term review of the gFSC | Reviewed and comments sent to GSU & posted on website

## Slide 3: SAG achievements (2)
Main activities planned | Progress Update
Clarify strategy of engagement into the global network against food crises | Clusters members attend on behalf of their agencies Info dissemination at the gFSC partner’s meeting Need to request FAO and WFP for a meeting about the strategy of engagement of NGOs within the global network.
Develop 2020-2022 strategy for the gFSC | One day SAG seminar on 21st May First draft outline of the Strategic Plan by late June Webinar to present the draft outline in early July Consultation launched with partners First draft strategy by end of September Final Strategy presented in November
Identify priorities and needs of support from country clusters | ToRs developed, Surveys conducted, Initial report out Initial findings reported back in plenary Need to produce SAG recommendations by late June
Learn lessons from the CCPM | CCPM report not received (16 out of 26)

## Slide 4: SAG achievements (3)
Main activities planned | Progress Update
Develop partnerships with the private sector | Bruno, as a panelist during the Humanitarian Week in February (Geneva) about interactions with the private sector Issue is parked at the moment
Develop the membership of the cluster | 63 members / 18 application to be reviewed
Livestock | Decision of having no technical working group, so far as not clear request from the country level, through the survey

## Slide 5: SAG members
Names | Agencies
Angela Hinrichs | FAO
Cyril Lekiefs | ACF (late 2019)
Carine Malardeau | IFRC (late 2019)
Bruno Minjauw | gFSC coordinator
Elisa Persico | WFP
Katie Rickard | Reach
Philippa Young | Oxfam
In between meetings, you are invited to share any information / concerns related to humanitarian coordination in FSL throughout this email address sag@fscluster.org and make ad hoc requests to SAG members.